## Cover
KANBAN BOARD
This is a free version of the "Kanban Board" spreadsheet. To download the complete resource, join You Exec Plus, and gain access to our entire library of spreadsheet models and business resources and receive new ones each week.
Start today
SYNOPSIS
Need a simple but effective workflow to manage your projects? Use our Kanban Board spreadsheet to visually track and organize a project's most important tasks. Easily view color-coded tasks according to their priority as they progress through your custom workflow category1 with a kanban visualization. Set work-in-progress limits, and bottlenecks will get flagged so no one stage gets overwhelmed. Keep tabs on upcoming deadlines with a color-coded 12-month calendar view. And a dashboard tracks your overall progress and overdue tasks, as well as the number of tasks by priority, by status, and assigned to each stakeholder.
EXPLAINER
Watch video
We value your input. If you have any comments, questions, or suggestions on how to improve this business resource please let us know.
Feedback
Errors and omissions liability (E&O): You Exec LLC makes no guarantee that the formulas, models, analysis, financial projections, estimates, graphs, reports, numbers, and any derivatives sourcing from this model are free of errors and omissions. Our financial modelers have audited this model to the best of their capabilities, yet You Exec LLC assumes no liability for erroneous outcomes derived from this financial model.
Copyright © You Exec LLC. All rights reserved.

## Table of contents
TABLE OF CONTENTS
1 | Cover
2 | Table of contents
3 | Task list
4 | Kanban board
5 | Fields
6 | Benefits
COLOR KEY
Types | Example | Description
User inputs | 3400 | User inputs
Calculations | 3400 | Formula results
Results
Good results | 3400 | Favorable outcomes
Bad results | 3400 | Unfavorable outcomes

## Task list
Back-End
TASK LIST
| Helpdesk Support Tracker | IT Support Tracker
|  | Task | Stage | Priority | Person responsible | Start date | Due date | Finish date | Work progress (%) | Work hours (#) | NOTES | Kanban_dropdown | Auxiliary
1 |  | Instalasi POS register Semesta Peslit | Complete | High | Buchori | 2024-08-21 | 2024-08-23 | 2023-08-29 | 100% | 122 | Double-click on date fields cells to edit in calendar view. | Task | Complete_01
2 |  | Stock Opname Agustus 2024 | Complete | Medium | All | 2024-08-01 | 2024-08-31 | 2024-08-31 | 100% | 120 | "Finish date" turns gray when toggled to done as a reminder to enter the date completed. | Person responsible | Complete_02
3 |  | Loading Persiapan Peslit Taman Ismail Marjuki 25 Agust 2024 | Complete | High | Buchiri, AAT, Pass | 2024-08-25 | 2024-08-25 | 2024-08-25 | 100% | 12 | Do not select all and delete or the formulas for the work progress bar will get deleted too. | Start date | Complete_03
4 |  | cancel SO-PO GAN, BKM,WAM yang tidak sama nilainya | Complete | Medium | Prasetyo | 2024-08-27 |  | 2024-09-24 | 100% |  |  | Due date | Complete_04
5 |  | Support Pesta Literasi & Semesta TIM 25-1 Sept 2024 | Complete | Medium | ALl | 2024-08-25 | 2024-08-25 | 2024-09-01 | 100% | 78 |  | Finish date
6 |  | Test Firewall Karawaci & BSD tanpa Proxy | Complete | Medium | Sumitro | 2024-09-02 | 2024-09-02 | 2024-09-16 | 100% |  |  | Work progress (%) | Complete_06
7 |  | Posting Statment Buln Agustus 2024 | Complete | High | All | 2024-09-02 | 2024-09-02 | 2024-09-02 | 100% | 24 |  |  | Complete_07
8 |  | Prosess Delivered So atas Order Online Agustus 2024 | Complete | High | All | 2024-09-02 | 2024-09-04 | 2024-09-09 | 100% | 35 |  | Work hours (#) | Complete_08
9 |  | Store In Store Yogya Sukabumi Suryakencana> 10499 Gramedia Sukabumi | Hold before final | Medium | Prasetyo | 2024-09-03 |  |  | 10% | Batal |  |  | Hold before final_01
10 |  | Store In Store Yogya Sumedang > 17110 Gramedia Subang | Hold before final | Medium | Prasetyo | 2024-09-03 |  |  | 10% | Batal |  |  | Hold before final_02
11 |  | Store In Store Transamart Kota Casablanca > 10108 Matraman | Complete | High | Aat | 2024-09-03 | 2024-09-23 | 2024-09-30 | 100% |  |  |  | Complete_09
12 |  | BA Kesalahan Rcv 10478 Dwi Maju POGAM2408-00313744 >email Audina | Complete | Medium | Sumitro | 2024-09-05 | 2024-09-06 | 2024-10-09 | 100% |  |  |  | Complete_10
13 |  | Support Pameran Gramedia Sale Resinda Karawang 14- 30 Sept 2024 | Complete | Medium | Aat | 2024-09-13 | 2024-09-14 | 2024-09-30 | 100% |  |  |  | Complete_11
14 |  | Support Pameran Gramedia Sale Botani Atrium Mall 23-Sept-6 Okt 2024 | Complete | Medium | Widiarto | 2024-09-15 | 2024-09-23 | 2024-10-06 | 100% |  |  |  | Complete_12
15 |  | Persiapan Penerimaan Gramedia The Park Sawangan 10174 di Depok | Complete | Medium | Widiarto | 2024-09-06 | 2024-09-15 | 2024-10-23 | 100% |  |  |  | Complete_13
16 |  | Case Retturn So 10124 yang Nilainya tidak Sama dengan Invoice | Complete | Medium | Rofiq | 2024-09-09 | 2024-09-12 | 2024-09-13 | 100% |  |  |  | Complete_14
17 |  | Relokasi 10127 Gramedia yogya mallioboro 12 Sept sudah Close | Complete | Medium | Adi S | 2024-09-12 |  | 2025-01-08 | 100% |  |  |  | Complete_15
18 |  | Migrasi Event1 to 81112 di JGC 27 Opname , 1 Oktober Migrasi ke 81112 | Complete | Medium | Buchori | 2024-09-10 | 2024-09-29 | 2024-10-01 | 100% |  |  |  | Complete_16
19 |  | Relokasi 10127 Gramedia yogya mallioboro 12 Sept sudah Close Opening 6 des 2024 | Complete | Medium | Adi S | 2024-09-04 |  | 2024-12-06 | 100% |  |  |  | Complete_17
20 |  | Support Relokasi Cirebon Grage 10142 Opening 1 okt 2024 | Complete | High | Adi S | 2024-09-03 | 2024-09-30 | 2024-10-03 | 100% |  |  |  | Complete_18
21 |  | Store In Store Transamart Central Park-> 10452 Gramedia Central Park | Complete | High | Buchori | 2024-09-08 | 2024-10-01 | 2024-10-01 | 100% |  |  |  | Complete_19
22 |  | Relokasi 10142 Gramedia Cirebon Cipto Re Opening 3 Okt 2024 | Complete | High | Adi S |  | 2024-10-03 | 2024-10-03 | 100% |  |  |  | Complete_20
23 |  | Reopening Gramedia Kendari 10182 25 Oktober 2024 | Complete | High | Muchsin |  | 2024-10-25 | 2024-10-25 | 100% |  |  |  | Complete_21
24 |  | Store In Store Gramedia di UMN ( by WS Gramedia SMS ) | Complete | High | Sumitro | 2024-09-03 | 2024-10-02 | 2024-10-02 | 100% |  |  |  | Complete_22
25 |  | support Event Sainsday Pim3 7-12 Okt 2024 | Complete | Medium | Agung | 2024-10-02 | 2024-10-06 | 2024-09-12 | 100% |  |  |  | Complete_23
26 |  | Support Event Pop & Shop MM Bekasi 7 s/d 13 Okt 2024 | Complete | Medium | Sutono | 2024-10-02 | 2024-10-06 | 2024-10-13 | 100% |  |  |  | Complete_24
27 |  | Support Event Gramedia Sale 7 s/d 27 Okt 2024 Karawaci | Complete | Medium | Sumitro | 2024-10-02 | 2024-10-04 | 2024-10-30 | 100% |  |  |  | Complete_25
28 |  | Support Event Gramedia Sale 11 s/d 20 Okt 2024 matraman di FCC Fatmawati | Complete | Medium | Aat | 2024-10-02 | 2024-10-10 | 2024-10-20 | 100% |  |  |  | Complete_26
29 |  | Support Event Store Superindo Pulomas ( Pic Gramedia ARTHA GADING ) | In-Progress | Medium | Buchori | 2024-10-02 | 2025-05-15 | 2025-07-01 | 100% |  |  |  | In-Progress_01
30 |  | Persiapan Penerimaaan Product Gramedia Buah Batu 10174 d GwK minggu ke 3 Okt | Complete | Medium | Sutono | 2024-10-04 | 2024-10-15 |  | 100% |  |  |  | Complete_27
31 |  | Persiapan Penerimaan Product Gramedia Grand Wisata 10132 | Complete | Medium | Priyanta | 2024-10-04 | 2024-10-30 | 2025-02-09 | 100% |  |  |  | Complete_28
32 |  | Asessment AP & LAN PGI keluhakoneksi Lambat tidak setabil | Complete | Medium | Hamzah | 2024-11-26 |  | 2025-02-03 | 100% |  |  |  | Complete_29
33 |  | Persiapan Rcv Untuk Citraland Relokasi, di Graemdia Matramana Lt 4 | Complete | Medium | Buchori | 2024-11-28 | 2024-12-04 | 2024-12-05 | 100% |  |  |  | Complete_30
34 |  | Asessment LAN di Gramedia Online Tipar Cakung dampak non akltif Wh 40009 | Complete | Medium | Aat | 2024-12-04 |  | 2025-01-13 | 100% |  |  |  | Complete_31
35 |  | Instalasi Dynatools di Matraman Lt 3 Untuk Fullfillment Shoppe MKG mulai 10 Jan 2025 + Aplikasi release RFID | Complete | Medium | Buchori | 2024-12-05 |  | 2025-01-06 | 100% |  |  |  | Complete_32
36 |  | Persiapan Semesta Jawa timur ( Tunjungan Plaza 25-3 Jan | Complete | Medium | Priyanta | 2024-12-05 |  | 2025-01-05 | 100% |  |  |  | Complete_33
37 |  | Adjustemtn SO Banjarmasin Veteran | Complete | Medium | Rofiq | 2024-12-19 |  | 2024-12-24 | 100% |  |  |  | Complete_34
38 |  | Adjustemtn SO Semarang Majapahit | Complete | Medium | David A | 2024-12-19 |  | 2024-12-24 | 100% |  |  |  | Complete_35
39 |  | Adjustment SO Gramedia BSD | Complete | Medium | Sumitro | 2024-12-18 |  | 2024-12-23 | 100% |  |  |  | Complete_36
40 |  | Adjustment SO Gramedia Jember & Satelite | Complete | Medium | Edy S | 2024-12-23 |  | 2024-12-23 | 100% |  |  |  | Complete_37
41 |  | Adjustment SO Gramedia Pal Merah Barat | Complete | Medium | Agung | Des 31, 2024 |  | 2025-01-01 | 100% |  |  |  | Complete_38
42 |  | Adjustment SO Gramedia Batam | Complete | Medium | IVO | 2025-01-16 |  | 2025-01-20 | 100% |  |  |  | Complete_39
43 |  | Shipping ITGAM Dummy WH ke Semesta Jogja | Complete | Medium | Agung | 2025-01-16 |  | 2025-01-19 | 100% |  |  |  | Complete_40
44 |  | Ajustment SO Tahunan Medan Gajah Mada | Complete | Medium | Santo Gultom | 2025-01-13 |  | 2025-01-22 | 100% |  |  |  | Complete_41
45 |  | Peralihan Pameran Spark 10161 ke 10124 | Complete | Medium | Hendry | 2025-01-22 |  | 2025-02-05 | 100% |  |  |  | Complete_42
46 |  | Adjustment SOB 10127 Gramedia Jogja Malioboro | Complete | Medium | Adi S | 2025-01-29 |  | 2025-01-30 | 100% |  |  |  | Complete_43
47 |  | Cancel GRN POGAM2501-00299589 10124 Koordinasi dgn audit&buyer | Complete | Medium | Rofiq | 2024-10-03 |  | 2025-02-04 | 100% |  |  |  | Complete_44
48 |  | Adjustment Item Cleansing MNB1 10445 Gramedia Pondok Gede | Complete | Medium | Gusri | 2025-02-06 |  | 2025-02-06 | 100% |  |  |  | Complete_45
49 |  | Pemindahan Data, Email dll PC Anita Outdev | Complete | Medium | Aat | 2025-02-05 |  | 2025-02-10 | 100% |  |  |  | Complete_46
50 |  | Seting Koneksi Jaringan & Printer Perpindahan MD lt 3 & Prodev Lt 3 | Complete | Medium | Agung | 2025-02-10 |  | 2025-02-11 | 100% |  |  |  | Complete_47
51 |  | Seting Persiapan Pangkalan Bun di Graemdia Emerald | Complete | Medium | Agung | 2025-02-10 |  | 2025-02-11 | 100% |  |  |  | Complete_48
52 |  | Instalasi POS 365 untuk Semesta Palmerah Barat Regional B | Complete | Medium | Aat, Agung, Buchori | 2025-02-07 |  | 2025-02-10 | 100% |  |  |  | Complete_49
53 |  | Seting Persiapan Opening Gramedia Nipah Makasar di Petarani | Complete | Medium | Nuralam | 2025-02-07 |  | 2025-02-07 | 100% |  |  |  | Complete_50
54 |  | Instalasi & Support Opening Gramedia Grand Wisata Bekasi 10132 | Complete | High | Agung | 2025-02-11 |  | 2025-02-11 | 100% |  |  |  | Complete_51
55 |  | Stock opname RFID Gramedia.com Peralihan | Complete | High | Aat,Buchori | 2025-02-11 |  | 2025-02-13 | 100% |  |  |  | Complete_52
56 |  | Stock Opname RFID Gramedia PIM 18 & 25 Feb 2025 | Done | Medium | Agung | 2025-02-11 |  | 2025-02-18 | 100% |  |  |  | Done_01
57 |  | Cancel PO POGAM2412-00414886 Kesalaan Rcv 2 kali rcv | Complete | Medium | Prasetyo | 2025-02-12 |  | 2025-02-12 | 100% |  |  |  | Complete_53
58 |  | Stock Opname RFID Gramedia Grand Indonesia 27 Feb 2025 | Complete | High | Agung | 2025-02-27 |  | 2025-02-27 | 100% |  |  |  | Complete_54
59 |  | Adjustment IT Gramedia sentra Bandung, Palmerah | Complete | Medium | Raden Fadly | 2025-04-29 |  | 2025-04-29 | 100% |  |  |  | Complete_55
60 |  | Maintenance gudang / bersih - bersih gudang | Complete | Medium | Raden Fadly | 2025-05-07 |  | 2025-05-07 | 100% |  |  |  | Complete_56
61 |  | Instalasi printer di ruang wholesale | Complete | Medium | Hamzah, Raden Fadly | 2025-04-29 |  | 2025-04-29 | 100% |  |  |  | Complete_57
62 |  | Adjustment SO Gramedia Kudus | Complete | Medium | Raden Fadly | 2025-04-28 |  | 2025-04-28 | 100% |  |  |  | Complete_58
63 |  | Adjustment SO Gramedia Jombang, Pasuruan, Food Hall, Aeon JGC, Aeon Sentul, Kasablanka, Cinunuk, Pakuwon, SM Bandung | Complete | Medium | Raden Fadly | 2025-05-07 |  | 2025-05-09 | 100% |  |  |  | Complete_61
64 |  | Adjustment SO Gramedia Serpong, Kokas, Klaten, Central Park, UMM | Complete | Medium | Raden Fadly | 2025-05-13 |  | 2025-05-15 | 100% |  |  |  | Complete_60
65 |  | Instalasi Fresh CPU Untuk kebutuhan toko | Complete | Medium | Hamzah, Raden Fadly | 2025-05-05 |  | 2025-05-06 | 100% |  |  |  | #REF!
66 |  | Intalasi wintec untuk kebutuhan toko | Complete | Medium | Raden Fadly | 2025-05-07 |  | 2025-05-14 | 100% |  |  |  | Complete_62
67 |  | Instalasi dan Troubelshoot Printer di ruang markom, Bongkar dan rakit kabel LAN | Complete | Medium | Hamzah, Raden Fadly | 2025-05-15 |  | 2025-05-15 | 100% |  |  |  | Complete_63
68 |  | Konfigurasi IP Static di ruang Markom | Done | High | Hamzah, Raden Fadly | 2025-05-05 |  | 2025-05-06 | 100% |  |  |  | Done_02
70 |  | Penambahan Location Event 4 Store 10187 | Done | Medium | Buchori | 2025-05-15 |  | 2025-05-19 | 100% |  |  |  | Done_03
71 |  | ADjustment Perpindahan Label RFID 30001 ke 20003 | Complete | Medium | Prasetyo | 2025-05-15 | 2025-05-15 | 2025-05-15 | 100% |  |  |  | Complete_64
72 |  | Reset Email Gam227@gramedia.com | Done | Medium | Prasetyo | 2025-05-15 | 2025-05-15 |  | 100% |  |  |  | Done_04
73 |  | Posting Counting Grmedia Pangkalan Bun 17122 | Complete | Medium | Prasetyo | 2025-05-15 | 2025-05-15 | 2025-05-15 | 100% |  |  |  | Complete_65
74 |  | Penambahan Location Perpustakaan Mini SMM di Store 10105 Jogja Sudirman | Complete | Medium | David A | 2025-05-15 | 2025-05-15 | 2025-05-15 | 100% |  |  |  | Complete_66
75 |  | Pendataan Device Register Aktiff terkait Licensi 365 bln Agustus 2025 | Done | High | Prasetyo | 2025-05-14 | 2025-05-14 | 2025-06-04 | 100% |  |  |  | Done_05
76 |  | Penambahan Lines IJ Ownership Change menjadi 400 lines Uji coba | Done | Medium | Prasetyo | 2025-05-14 | 2025-05-15 | 2025-05-15 | 100% |  |  |  | Done_06
77 |  | MOvmennt Item Sampel permintaan MArkom IJGLK2505-000000897 | Done | Medium | Prasetyo | 2025-05-15 | 2025-05-15 | 2025-05-19 | 100% |  |  |  | Done_07
78 |  | ADjustment OUT GLKU Request Raja Item proyek | Done | Medium | Prasetyo | 2025-05-15 | 2025-05-15 | 2025-05-19 | 100% |  |  |  | Done_08
79 |  | Rcv TOGAN2505-000000027 erorr 'No lines for posting Update has been canceled' | Complete | Medium | Sutono | 2025-05-14 | 2025-05-15 | 2025-05-15 | 100% |  |  |  | Complete_67
80 |  | Adjustment SO Gramedia Santoso Jaya | Complete | Medium | Raden Fadly | 2025-05-16 |  | 2025-05-16 | 100% |  |  |  | Complete_68
81 |  | Ganti ID Orin SO Gramedia Ekalokasari | Complete | Medium | Raden Fadly | 2025-05-16 |  | 2025-05-16 | 100% |  |  |  | Complete_69
82 |  | Pembatalan IJ atas COR 40009 Status Open Order | Complete | High | Raden Fadly, Agung | 2025-05-16 |  | 2025-05-16 | 100% |  |  |  | Complete_70
83 |  | Cancel Product Rcv POGAM2504-00223097 | Complete | Medium | Prasetyo | 2025-05-18 | 2025-05-19 | 2025-05-19 | 100% |  |  |  | Complete_71
84 |  | Perpindahan data / backup di PC Wholesale | Complete | Medium | Raden Fadly | 2025-05-19 |  | 2025-05-19 | 100% |  |  |  | Complete_72
85 |  | Pnambahan location event4 Store 10117 | Done | Medium | Sumitro | 2025-05-19 | 2025-05-19 | 2025-05-19 | 100% |  |  |  | Done_09
86 |  | Adjustment Out Item Sample GLKU 80001 Req Raja | Complete | Medium | Prasetyo | 2025-05-20 | 2025-05-20 | 2025-05-20 | 100 |  |  |  | Complete_73
87 |  | Create Revenue Shareing Calculation 10478 Tgl 19 Mei 2025 | Complete | Medium | Prasetyo | 2025-05-20 | 2025-05-20 | 2025-05-20 | 100% |  |  |  | Complete_74
88 |  | Adjustment SO Gramedia Subang | Complete | Medium | Raden Fadly | 2025-05-20 |  | 2025-05-20 | 100% |  |  |  | Complete_75
89 |  | Troubleshoot printer showroom | Complete | Medium | Priyanta | 2025-05-19 |  | 2025-05-20 | 100% |  |  |  | Complete_76
90 |  | Adjustment Stock Opname Tahunan Gramedia HI 10372 | Done | Medium | Buchori | 2025-05-18 | 2025-05-25 | 2025-05-28 | 100% |  |  |  | Done_10
91 |  | Adjustment Stock Opname Tahunan Gramedia MM Bekasi 10123 | Done | Medium | Buchori | 2025-05-19 | 2025-05-23 | 2025-05-27 | 100% |  |  |  | Done_11
92 |  | Adjustment Stock Opname Tahunan Gramedia Pejaten 10454 | Done | Medium | Agung | 2025-05-19 |  | 2025-06-09 | 100% |  |  |  | Done_12
93 |  | Countin In Stock Nol Penjualan Siplah 19 Mei 2025 Gramedia Depok | Complete | Medium | Widiarto | 2025-05-19 | 2025-05-21 | 2025-05-21 | 100% |  |  |  | Complete_77
94 |  | Penghapusan Item Broken Gramedia Kediri 10438 | Complete | Medium | edy | 2025-05-19 | 2025-05-19 | 2025-05-21 | 100% |  |  |  | Complete_78
95 |  | Clone disk PC Wholesale | Complete | Medium | Hamzah, Raden Fadly | 2025-05-21 |  | 2025-05-21 | 100%
96 |  | Instalasi laptop baru GAM | Complete | Medium | Hamzah, Raden Fadly | 2025-05-21 |  | 2025-05-21 | 100%
97 |  | ADjutment Selisih Persediaan Gramedia Purwokerto Rita 10167 by Risma | Complete | Medium | David A | 2025-05-21 | 2025-05-21 | 2025-05-21 | 100%
98 |  | Install GMR di 3 PC Baru Cakung by Anydesk | Complete | Medium | AAT | 2025-05-21 | 2025-05-21 | 2025-05-21 | 100%
99 |  | Install GMR di PC Kelapagading Di Pintu Air 10.211.11.47 | Complete | Medium | Aat | 2025-05-21 | 2025-05-21 | 2025-05-21 | 100%
100 |  | Penyelesaian Kesalahan Rcv POGAM2505-00211979 10101 Pintu Air | Done | Medium | Buchori | 2025-05-21 |  | 2025-06-03 | 100%
101 |  | Set up PC pinjaman untuk TAB | Complete | Medium | Raden Fadly | 2025-05-22 |  | 2025-05-23 | 100%
102 |  | Adjustment ITGAM2505-000011413 status gagal shipping | Complete | Medium | Raden Fadly | 2025-05-23 |  | 2025-05-23 | 100%
103 |  | Instalasi printer di ruang markom (aktivation) | Complete | Medium | Hamzah, Raden Fadly | 2025-05-23 |  | 2025-05-23 | 100%
104 |  | Setting PC pinjaman untuk Matraman | Complete | Medium | Raden Fadly | 2025-05-23 |  | 2025-05-23 | 100%
105 |  | Seting Register Pinjaman Persiapan TAB Matraman | Done | Medium | Aat | 2025-05-23 | 2025-05-26 | 2025-06-03 | 100%
106 |  | Adjustment In Estudee Stationery Pack | Complete | Medium | Prasetyo | 2025-05-26 | 2025-05-26 | 2025-05-26 | 100%
107 |  | Packing PC pinjaman untuk Matraman | Complete | Medium | Raden Fadly | 2025-05-26 | 2025-05-26 | 2025-05-27 | 100%
108 |  | Setting dogle wifi di gedung sebrang ruangan digital lt 5 | In-Progress | Medium | Hamzah, Raden Fadly | 2025-05-26 |  | 2025-05-27 | 100% |  |  |  | In-Progress_02
109 |  | Adjustment IT Gramedia Cimahi Mall | Complete | Medium | Raden Fadly | 2025-05-26 |  | 2025-05-27 | 100% |  |  |  | Complete_90
110 |  | Adjustment IT Gramedia Bojonegoro | Complete | Medium | Raden Fadly | 2025-05-26 |  | 2025-05-26 | 100% |  |  |  | Complete_91
111 |  | Adjustment IT Wholesale Transit Dummy Warehouse (TW3) | Complete | Medium | Raden Fadly | 2025-05-26 |  | 2025-05-26 | 100%
112 |  | Adjustment SO Gramedia BBC Palasari | Complete | Medium | Raden Fadly | 2025-05-26 |  | 2025-05-26 | 100%
113 |  | Reset printer di lt 2 ruang cash and bank | Complete | Medium | Raden Fadly | 2025-05-26 |  | 2025-05-26 | 100%
114 |  | Installasi office 2021 user hr.nina | Complete | Medium | Hamzah, Raden Fadly | 2025-05-27 |  | 2025-05-27 | 100%
115 |  | Troubelshoot printer di showroom | Complete | Medium | Raden Fadly | 2025-05-27 |  | 2025-05-27 | 100%
116 |  | Adjustment SO Gramedia Yogya Lembang | Complete | Medium | Raden Fadly | 2025-05-27 |  | 2025-05-27 | 100%
117 |  | Adjustment SO Gramedia Yogya Lembang | Complete | Medium | Raden Fadly | 2025-05-28 |  | 2025-05-28 | 100%
118 |  | Adjustment SO Gramedia Yogya Lembang | Complete | Medium | Raden Fadly | 2025-05-28 |  | 2025-05-28 | 100%
119 |  | Delete Journal Lines untuk proses pembatalan IT | Complete | Medium | Raden Fadly | 2025-05-30 |  | 2025-05-30 | 100%
120 |  | Stock Opname Pameran Kuningan City (10180) | Complete | Medium | Agung | 2025-05-12 |  | 2025-05-12 | 100%
121 |  | Adjustment SO Gramedia Casablanca | Complete | Medium | Raden Fadly | 2025-05-08 |  | 2025-05-08 | 100%
122 |  | Adjustment SO Gramedia Yogya Cinunuk, Pakuwon, SM Bandung | Complete | Medium | Raden Fadly | 2025-05-09 |  | 2025-05-09 | 100%
123 |  | Ganti ID Orin SO Customer Multimedia Nusantara | Complete | Medium | Raden Fadly | 2025-05-30 |  | 2025-05-30 | 100%
124 |  | Adjustment SO Gramedia Palmerah Barat | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
125 |  | Adjustment IT di warehouse DW00003609 | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
126 |  | Setting printer tidak bisa print di lantai 5 ruang GPU | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
127 |  | Adjustment SO warehouse DW00000738 | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
128 |  | ADjustment Stock Opname Lippo Puri 10407 | Complete | Medium | Sumitro | 2025-05-07 | 2025-05-28 | 2025-05-28 | 100%
129 |  | Adjustemnt Stock Opname Nonbooks 10108 | Done | Medium | Buchori | 2025-06-03 |  | 2025-06-09 | 100%
130 |  | Adjjstment Stock Opname 10178 SMS | Done | Medium | Sumitro | 2025-06-04 | 2025-06-06 | 2025-06-09 | 100%
131 |  | Adjustment Out 40009 _req Audit | Done | Medium | Prasetyo | 2025-06-02 | 2025-06-04 | 2025-06-25 | 100%
132 |  | ADjustment IN MG 10115,10108,10117,10150 Keperluan MP_Berta | Complete | Medium | Prasetyo | 2025-06-04 | 2025-06-04 | 2025-06-04 | 100%
133 |  | Gramedia ThePark Sawangan Erorr GMR saat mau Input Return to DC | Complete | Medium | Widiarto | 2025-06-05 | 2025-06-05 | 2025-06-05 | 100%
134 |  | Seting EVENT Register Pameran Gramedia Cibubur 10428-71 ke event1 | Complete | Medium | Widiarto | 2025-06-05 | 2025-06-05 | 2025-06-05 | 100%
135 |  | Adjustment Pecah ITem di Wh 20003 | Complete | Medium | Prasetyo | 2025-06-09 | 2025-06-09 | 2025-06-09 | 100%
136 |  | Koreksi BA Salh Rcv 10445 Gramedia Pondok Gede POGAM2505-00347282 | Complete | Medium | Gusr | 2025-06-04 | 2025-06-06 | 2025-06-09 | 100%
138 |  | Adjutment Stock Opname 10486 Graemdia Jogja City Mall 2025 | Complete | Medium | Adi S | 2025-06-09 |  | 2025-06-12 | 100%
139 |  | Adjustment IT Gramedia Retail | Complete | Medium | Raden Fadly | 2025-06-10 |  | 2025-06-10 | 100%
140 |  | Adjustment IT di warehouse 18011 | Complete | Medium | Raden Fadly | 2025-06-09 |  | 2025-06-09 | 100%
141 |  | Adjustment SO Gramedia Palmerah Barat | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
142 |  | Adjustment IT di warehouse DW00003609 | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
143 |  | Adjustment SO warehouse DW00000738 | Complete | Medium | Raden Fadly | 2025-06-02 |  | 2025-06-02 | 100%
144 |  | Adjustemnt Stock Opname 10152 Gramedia Panakukang 2025 | Complete | Medium | Nuralam | 2025-06-11 |  | 2025-06-15 | 100%%
145 |  | Adjustemnt Stoock Opname 10151 Graemdia Semarang majapahit 2025 | Complete | Medium | David A | 2025-06-11 |  | 2025-06-17 | 100%%
146 |  | Adjustment IT di warehouse DW00003469 | Complete | Medium | Raden Fadly | 2025-06-11 |  | 2025-06-11 | 100%
147 |  | Adjusment SO di warehouse DW00000769 | Complete | Medium | Raden Fadly | 2025-06-11 |  | 2025-06-11 | 100%
148 |  | Shipping ITGAM2506-000004722 10123 Gagal atas item 724070329 | Complete | Medium | Prasetyo | 2025-06-12 | 2025-06-12 | 2025-06-13 | 100%
149 |  | Adjustment SO Gramedia Kasablanka, Klaten, WH D000003913 | Complete | Medium | Raden Fadly | 2025-06-12 |  | 2025-06-12 | 100%
150 |  | Adjustment IT di warehouse DW00003469 | Complete | Medium | Raden Fadly | 2025-06-12 |  | 2025-06-12 | 100%
151 |  | Adjustment SO di warehouse D000003913 | Complete | Medium | Raden Fadly | 2025-06-13 |  | 2025-06-13 | 100%
152 |  | Perpindahan item dari selisih ke general di warehoue wholesale | Complete | Medium | Raden Fadly | 2025-06-13 |  | 2025-06-13 | 100%
153 |  | Instalasi ulang PC dan Laptop user wholesale | Complete | Medium | Raden Fadly | 2025-06-12 |  | 2025-06-13 | 100%
154 |  | Adjustment SO di warehouse D000003913, DW00000360 | Complete | Medium | Raden Fadly | 2025-06-16 |  | 2025-06-16 | 100%
155 |  | Adjustment SO Mitra Gramedia.com | Complete | Medium | Raden Fadly | 2025-06-19 |  | 2025-06-19 | 100%
156 |  | Adjusment SO Tahunan 2025 Sorong | Complete | Medium | Muchsin | 2025-06-23 |  | 2025-06-23 | 100%
157 |  | Adjusment SO Tahunan 2025 Ternate | Complete | Medium | Muchsin | 2025-06-24 |  | 2025-06-24 | 100%
158 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Paragon Sorong | Complete | Medium | Muchsin | 2025-06-18 |  | 2025-06-18 | 100%
159 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Tarakan | Complete | Medium | Muchsin | 2025-06-23 |  | 2025-06-23 | 100%
160 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Lippo Mall Kupang 10130-72 | Complete | Medium | Muchsin | 2025-06-20 |  | 2025-06-20 | 100%
161 |  | Adjustment OUT GLK Request Risma | Complete | Medium | Prass | 2025-06-25 | 2025-06-25 | 2025-06-25 | 100%
162 |  | Return SOGAM2506-00102741 &SOGAM2506-00126844 | Done | Medium | Agung | 2025-07-25 | 2025-06-26 | 2025-06-26 | 100%
163 |  | Adjustment SO Gramedia Aceh | Complete | Medium | Raden Fadly | 2025-06-24 |  | 2025-06-24 | 100%
164 |  | Adjustment SO Gramedia Kudus | Complete | Medium | Raden Fadly | 2025-06-25 |  | 2025-06-25 | 100%
165 |  | Pembongkaran Server Toko, Memastikan Backup sudah dicopy, Mematikan Server dan memandu pembongkaran Server Papua | Complete | Medium | Muchsin | 2025-06-23 |  | 2025-06-23 | 100%
166 |  | Pembongkaran Server Toko, Memastikan Backup sudah dicopy, Mematikan Server dan memandu pembongkaran Server Kendari | Complete | Medium | Muchsin | 2025-06-24 |  | 2025-06-24 | 100%
167 |  | Setting Printer TM82MX, Ganti Hardware Profiler dan Test Health Mesin 10459-01 Toko Ternate | Complete | Medium | Muchsin | 2025-06-30 |  | 2025-06-30 | 100%
168 |  | Instal Laptop Toko dgn aplikasi Kasir dan Activasi StoreCommerce untuk Mesin Pameran Lippo Mall Kupang 10130-73 | Complete | Medium | Muchsin | 2025-06-26 |  | 2025-06-26 | 100%
169 |  | Adjustment SO Gramedia Serpong | Complete | Medium | Raden Fadly | 2025-06-30 |  | 2025-06-30 | 100%
170 |  | Menghapus IP static di ruang markom | Complete | High | Hamzah, Raden | 2025-06-30 |  |  | 100%
171 |  | Adjustment SO Location gramedia.com | Complete | Medium | Raden Fadly | 2025-07-02 |  | 2025-07-02 | 100%
172 |  | Adjustment SO Kinokunia | Complete | Medium | Raden Fadly | 2025-07-02 |  | 2025-07-02 | 100%
173 |  | Adjustment ITGAM2507-000002680 Gagal shipping | Complete | Medium | Raden Fadly | 2025-07-07 |  | 2025-07-07 | 100%
174 |  | Adjusment SO Gramedia Solo, Puwodadi | Complete | Medium | Raden Fadly | 2025-07-07 |  | 2025-07-07 | 100%
175 |  | Adjustment SO Gramedia Yogya Cinunuk, LP NBS UMM, LP DUNIA ILMU | Complete | Medium | Raden Fadly | 2025-07-08 |  | 2025-07-08 | 100%
176 |  | Perpindahan atas no item 591801583 dari event1 ke general di warehouse 18010 | Complete | Medium | Raden Fadly | 2025-07-08 |  | 2025-07-08 | 100%
177 |  | Adjustemnt OUT Broken, Selisih DC Persiapan SO DC | Complete | Medium | Prasetyo | 2025-08-08 |  | 2025-08-04 | 100%
178 |  | Adjutsment Pemakaian BPR BOD Product GLKU 80001 | Complete | Medium | Prasetyo | 2025-08-08 |  | 2025-08-04 | 100%
179 |  | Adjustment OUT Pemakaian Marketing Promosi GLKU 80001 | Complete | Medium | Prasetyo | 2025-08-07 |  | 2025-08-04 | 100%
180 |  | Testing Aplikasi New Opn DC Cakung | Complete | Medium | Prasetyo | 2025-08-08 |  | 2025-08-04 | 100%
181 |  | Instalasi APlikasi New Opn DC Cakung | Done | Medium | Aat | 2025-08-05 |  | 2025-08-08 | 100%
182 |  | Penutupan GS Togamas WR Supratman | Complete | Medium | Sutono | 2025-08-15 |  | 2025-08-30 | 100%
183 |  | Penutupan Gramedia Cijantung 10179 | Pending | Cancelled | Agung | 2025-09-09
184 |  | Support SEMESTA Gramedia Botani 29 sept-12 okt 2025 Atrium Mall Botani Square 6 Reg+2 Info | Complete | Medium | Widiarto | 2025-09-22 |  | 2025-06-19 | 100%
185 |  | Support SEMESTA Gramedia Bintaro Plaza 5 regsiter+Modem+Switch | Done | Medium | Agung | 2025-09-20 |  | 2025-06-22 | 100%%
186 |  | Pemindahan Stock 81108 General Ke EVent1 general akan di pake Semesta | Done | Medium | Buchori | 2025-09-10 |  | 2025-09-17 | 100%
187 |  | Support SEMESTA MM Bekasi 22 Sept - 14 Okt 2025 | Complete | Medium | Aat | 2025-09-15 |  | 2025-09-19 | 100%
188 |  | Adjustment Stock Opname Lampung Raden Inten | Done | Medium | Buchori | 2025-09-15 | 2025-09-17 | 2025-09-18 | 100%
189 |  | Shipping > ITGAM2509-000016364 & ITGAM2509-0000163 counting Stock Kurang | Done | Medium | Raden Fadly | 2025-09-18 |  | 2025-09-19 | 100%
190 |  | Adjustemnt Pemakaian Label RFID Matraman agust-Sept 2025 | Done | Medium | Prasetyo | 2025-09-17 |  | 2025-09-19 | 100%
191 |  | Adjustement Koloni di Entity GPU | Done | Medium | Prasetyo | 2025-09-22 | 2025-09-23 | 2025-09-23 | 100%
192 |  | Adjusment Sample GLKU _ Raja | Done | Medium | Prasetyo | 2025-09-22 | 2025-09-23 | 2025-09-23 | 100%
193 |  | Drawer Pameran IBF 10489 Tidak bisa Berfungsi/Terbuka | Done | Medium | Sumitro | 2025-09-25 |  | 2025-09-25 | 100%
194 |  | ITGAM Erorr ketika di Shiping 10227 to 10108 | Done | Medium | Prasetyo | 2025-09-24 | 2025-09-25 | 2025-09-25 | 100%
195 |  | Move Label RFID 30001 to 20003 130000 By Fikri Audit | Done | Medium | Prasetyo | 2025-09-25 |  | 2025-09-25 | 100%
196 |  | Shipping IT 10242 to GWS 11197 | Done | Medium | Raden Fadly | 2025-09-25 |  | 2025-09-26 | 100%
197 |  | Perubahan Snapshoot Hanya Owner V untuk Item Konsinyasi | Done | Medium | Prasetyo | 2025-09-25 |  | 2025-09-25 | 100%
198 |  | Adjustemnt TW1 Sisi Pnerbit atas ITGAM2509-000013490 | Done | Medium | Prasetyo | 2025-09-26 |  | 2025-09-26 | 100%
199 |  | Adjustement PGI atas Omset DJOJO & Pameran Afair | Done | Medium | Agung | 2025-09-26 |  | 2025-09-26 | 100%
200 |  | Invoicing LP SOGAM2509-00181454 | Done | Medium | Raden Fadly | 2025-09-26 |  | 2025-09-26 | 100%
201 |  | Penyelesain Kesalahan Rcv COGAM2508-000025066 | Done | Medium | Rofiq | 2025-09-25 |  | 2025-09-26 | 100%
202 |  | Penyelesaian Kesalahan Rcv POGAM2509-00117717 | Done | Medium | Prasetyo | 2025-09-24 |  | 2025-09-26 | 100%
203 |  | Koreksi BA Salh Rcv POGAM2502-00136228 | Done | Medium | Sutono | 2025-09-30 |  | 2025-09-30 | 100%
204 |  | Adjustment Hasil SO Gramedia AEON 10478 | Done | Medium | Sumitro | 2025-10-01 |  | 2025-10-03 | 100%
205 |  | Adjustment Hasil SO Gramedia Tarakan 10176 | Done | Medium | Muchsin | 2025-10-06 |  | 2025-10-09 | 100%
206 |  | Adjustemnt Hasil SO Gramedia Pontianak Gaia 10121 | Done | Medium | Hendry | 2025-10-06 |  | 2025-10-09 | 100%
207 |  | ADjustment Hasil SO Gramedia Samarinda Lembuswana 10148 | Done | Medium | ROfiq | 2025-10-10 |  | 2025-10-11 | 100%
208 |  | ADjustment Hasil SO Gramedia Pekan Baru Mall 10172 | Done | Medium | IVO | 2025-10-15 |  | 2025-10-27 | 100%
209 |  | Penghapusan Item Btoken 10109 Medan Gajah Mada | Done | Medium | Santo Gultom | 2025-10-16 |  | 2025-10-19 | 100%
210 |  | Adjustment Hasil Opname Gramedia Karawang Galuh 10435 | Done | Medium | Priyanta | 2025-10-16 |  | 2025-10-20 | 100%
211 |  | Adjustemnt Hasil SO Gramedia Cibubur 10428 | Done | Medium | Widiarto | 2025-10-14 |  | 2025-10-16 | 100% |  |  |  | Done_45
212 |  | Adjustment Hasil SO The Park Sawangan 10222 | Done | Medium | Widiarto | 2025-10-22 |  | 2025-10-24 | 100%
213 |  | Persiapan Support Semesta Jakarta FX Sudirman 25-2 Nov 2025 | Done | Medium | Aat | 2025-10-21 |  | 2025-10-24 | 100%
214 |  | Setup POS PGI untuk Event FUmi Kuro 25 Okt 2025 di Ice BSD | Done | Medium | Aat | 2025-10-21 |  | 2025-10-23 | 100%
215 |  | Adjustment Hasil SO Gramedia Sudirman Jogja 10105 | Done | Medium | David A | 2025-10-24 |  | 2025-10-30 | 100%
216 |  | Adjustment Hasil SO Gramedia Bengkulu Meranti 10469 | Done | Medium | Gusri | 2025-10-24 |  | 2025-10-24 | 100%
217 |  | Adjustment OUT atas Item Aset Terjual BSW | Done | Medium | Prasetyo | 2025-10-26 |  | 2025-10-28 | 100%
218 |  | Adjustment Hasil SO Gramedia Emporium Pluit 10187 | Done | Medium | Buchori | 2025-10-29 |  | 2025-11-02 | 100%
219 |  | Adjustment Out Expo The Park (Terdampak Kebakaran) 10182 Kendari | Done | Medium | Muchsin | 2025-10-31 |  | 2025-11-02 | 100%
220 |  | Pembongkaran Server Toko, Memastikan Backup sudah dicopy, Mematikan Server dan memandu pembongkaran Server Ternate | Done | Medium | Muchsin | 2025-07-05 |  |  | 100%
221 |  | Pembongkaran Server Toko, Memastikan Backup sudah dicopy, Mematikan Server dan memandu pembongkaran Server Kupang | Done | Medium | Muchsin | 2025-10-10 |  |  | 100%
222 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Ternate | Done | Medium | Muchsin | 2025-07-11 |  |  | 100%
223 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Papua | Done | Medium | Muchsin | 2025-08-05 |  |  | 100%
224 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Maumere | Done | Medium | Muchsin | 2025-09-02 |  |  | 100%
225 |  | Install PC Kasir dan Activasi StoreCommerce untuk Mesin Pameran Ternate | Done | Medium | Muchsin | 2025-10-02 |  |  | 100%
226 |  | Adjustment Stok Opname Tang City BSD 81489 | Done | Medium | Sumitro | 2025-11-12 |  | 2025-11-14 | 100%
227 |  | Adjustment Stok Opname GCikarang | Done | Medium | Aat | 2025-11-12 |  | 2025-11-13 | 100%
228 |  | Adjustment Stork Opname Gramedia Emerald Bintaro 10161 | Done | Medium | Agung | 2025-11-14 |  | 2025-11-16 | 100%
229 |  | Adjustment Stock Opname Gramedia Pangkal Pinang 10210 | Done | Medium | Gusri | 2025-11-18 | 2025-11-18 | 2025-11-19 | 100%
230 |  | Adjustemnt BSW | Done | Medium | Prasetyo | 2025-11-24 |  | 2025-11-24 | 100%
231 |  | ADjustment SO Gramedia Padang 10114 | Done | Medium | ivo | 2025-12-02 |  | 2025-12-08 | 100%
232 |  | Adjustment Broken Waterlily | Done | Medium | Prasetyo | 2025-12-02 |  | 2025-12-02 | 100%
233 |  | Adjustment Broken Ternate (10459) | Done | Medium | Muchsin | 2025-11-10 |  | 2025-11-10 | 100%
234 |  | Adjustment Produk Broken & Expired Gramedia Kendari Lippo Plaza (10182) | Done | Medium | Muchsin | 2025-11-11 |  | 2025-11-11 | 100%
235 |  | Pengajuaan Adjustment Produk Credit_ Tarakan (10176) | Done | Medium | Muchsin | 2025-11-18 |  | 2025-11-18 | 100%
236 |  | Adjustment Penghapusan Barang Broken - 10176 | Done | Medium | Muchsin | 2025-11-27 |  | 2025-11-27 | 100%
237 |  | Penghapusan Item Broken Gramedia Maumere (10188) | Done | Medium | Muchsin | 2025-11-25 |  | 2025-11-25 | 100%
238 |  | ADjustement SO Partial 10372 Gramedia Harapan Indah | Done | Medium | Aat | 2025-12-03 |  | 2025-12-17 | 100%
239 |  | Adjustment SO Partial 10182 Gramedia Kendari Lippo | Done | Medium | Muchsin | 2025-12-10 |  | 2025-12-19 | 100%
240 |  | Adjustement SO Gramedia Bandung Merdeka 10104 | Done | Medium | Sutono | 2025-12-09 |  | 2025-12-12 | 100%
241 |  | Adjustemnt SO Gramedia Sidoarjo 10220 Pahlawan | Done | Medium | Andhiek | 2025-12-19 |  | 2025-12-21 | 100%
242 |  | Adjustment SO Gramedia Grand Mall Batam 10498 | Done | Medium | IVO | 2025-12-19 |  | 2025-12-24 | 100%
243 |  | Adjustment Stok Opname Gramedia Batam City Square 10165 | Done | Medium | IVO | 2025-12-18 |  | 2025-12-19 | 100%
244 |  | Adjustment Penghapusan Prodev atas pengajuan 16 Okt 2025 | Done | Medium | Prasetyo | 2025-12-23 |  | 2025-12-24 | 100%
245 |  | Journal IJGAM2602-000333877 has been posted. The selected item cannot be used in this context if it is associated with an Item model group where Always expensed is selected. Update has been canceled. Item number 723010099 does not exist. | Done | Medium | Agung | 2026-02-20 |  | 2026-02-20 | 100% | item reservation di nol kan
246 |  | TJ Balik & Cancel IJ Ownership & return SO atas kesalahan Testing MP multi | Done | Medium | Prasetyo | 2026-01-05 |  | 2026-01-07 | 100% | approve Audit
247 |  | GWS ITGAM2512-0000005785 & ITGAM2512-000005784 Tidak bisa Shipping | done | Medium | Aat | 2026-01-05 |  | 2026-01-05 | 100%
248 |  | Ekskalasi Kesalahan Rcv POGAM2512-00153548 | Done | Medium | Andhiek | 2026-01-05 |  | 2026-01-06 | 100%
249 |  | Pembatalan ITGAM2601-000001270 Grand Indonesia | Done | Medium | Agung | 2026-01-06 |  | 2026-01-06 | 100%
250 |  | Update Store COde atas Order Online Store 10221 yang tidak terbentuk SO, TJ nya sudah posted | Done | Medium | Prasetyo | 2026-01-06 |  | 2026-01-08 | 100%
251 |  | Adjustment Stok Opname Tahunan 17101 Gramedia Subang | Done | Medium | Sutono | 2026-01-06 |  | 2026-01-07 | 100%
252 |  | Koreksi SOPGI atas Penjualan Online SOPGI2512-00000276 | Done | Medium | Prasetyo | 2026-01-06 |  | 2026-01-06 | 100%
253 |  | DIsable atas Device MPOS ALL terkait Licensi 365 ( yang akan menggunakan untuk Aktivasi Kembali ) | Done | Medium | Hendry | 2026-01-06 |  | 2026-01-06 | 100%
254 |  | Penyelesaian SO gantung atas Order Onlien 11196 GWS | Done | Medium | Prasetyo | 2026-01-06 |  | 2026-01-08 | 100%
255 |  | Adjutsment In OUT di sisi GAM & Penerbit atas Penjualan Komik Kolian | Done | Medium | David A | 2026-01-06 |  | 2026-01-06 | 100%
256 |  | Adjustment IN DW00000769 atas SOGAM2601-00041973 | Done | Medium | Raden Fadly | 2026-01-07 |  | 2026-01-07 | 100%
257 |  | Ekskalasi & penyelesaian kesalahan Rcv POGAM2511-00162145 | Done | Medium | Hendry | 2026-01-07 |  | 2026-01-08 | 100%
258 |  | Implementasi & Instalasi Client dengan AV Sentineil One (S1) all Client HO & Store untuk menggantikan Eset yg berakhir di tgl 7 Jan 2026 | In-Progress | High | ALL | 2026-01-07
259 |  | Ekskalasi & Penyelesaain atas Order Online Tokopedia&tiktok gramedia Botani yang belum Naik ke 365 | Done | Medium | Widiarto | 2026-01-07 |  | 2026-01-08 | 100% | update Store Code
260 |  | Aktibasi Device Price Cheker di Gramedia Pamulang 17110 | Done | Medium | Sumitro | 2026-01-07 |  | 2026-01-08 | 100%
261 |  | Return SOSOGAM2601-00057236 Gramedia Medan gajah mada | Done | Medium | Santo Gultom | 2026-01-08 |  | 2026-01-08 | 100%
262 |  | Adjustment Stok Opname Gramedia 10103 Bali Galeria | Done | Medium | Mansyur | 2026-01-08 |  | 2026-01-10 | 100%
263 |  | Adjustment OUT INventory Persediaan di Customer Wholesale Retail Chanel&Distr yg sudah tidak aktiv | Done | Medium | Raden Fadly,Agung Dp | 2026-01-08 |  | 2026-01-10 | 100%
264 |  | Return SO SOGAM2601-00052730,SOGAM2601-00052731,SOGAM2601-00052732 Gramedia 10499 Sukabumi | Done | Medium | Santo Gultom | 2026-01-08 |  | 2026-01-08 | 100%
265 |  | Adjustemnt OUTProduct Food Expired Gramedia Pejaten 10454 | Done | Medium | Agung | 2026-01-08 |  | 2026-01-10 | 100%
266 |  | Seting Register Pameran 10473-71 Event1 Graemdia Cibinong City Mall | Done | Medium | Widiarto | 2026-01-08 |  | 2026-01-08 | 100%
267 |  | Perubahan Harga UP 20% Gramedia Maumere per 1 Feb 2026 mulai Pergantian Label | In-Progress | Medium | Muchsin | 2026-01-12
268 |  | Adjustment Item Broken GWS Tajem 11197 | Done | Medium | David A | 2026-01-12 |  | 2026-01-14 | 100%
269 |  | Aktivasi Device Mobile Pos SN: P21120CA00293 Gramedia Karawang Resinda 10133 | Done | Medium | Priyanta | 2026-01-12 |  | 2026-01-12 | 100%
270 |  | Pembuatan Location Event Gramedia Pollux Cikarang 17120 | Done | Medium | Priyanta | 2026-01-12 |  | 2026-01-12 | 100%
271 |  | Penyelesaian BA kesalahan Rcv COGAM2512-000019596 10488 | Done | Medium | Gusri | 2026-01-13 |  | 2026-01-14 | 100%
272 |  | Penyelesaian Item Lebih di GWS 11196 | In-Progress | Medium | Prasetyo | 2026-04-27
273 |  | Journal Counting Balik atas kesalahan Counting Wh 10474 | Done | Medium | Nuralam | 2026-01-13 |  | 2026-01-14 | 100%
274 |  | Request Counting 572190015 DW00000811 Wholesale | Done | Medium | Raden Fadly | 2026-01-14 |  | 2026-01-14 | 100%
275 |  | Adjustment OUT Close Store 10451 Gramedia Teras Kota | Done | Medium | Sumitro | 2026-01-11 |  | 2026-01-14 | 100%
276 |  | Kesalahan Rcv COGAM2512-000019596 Bengkulu Meranti | Done | Medium | Gusri | 2026-01-12 |  | 2026-01-14 | 100%
277 |  | Followup Salah WH atas Order Online Shoppee 10428 Cibubur masuk Ke WH nya Kupang | Done | Medium | Muchsin | 2026-01-13 |  | 2026-01-16 | 100% | Kesalahan Seting Wh
278 |  | Deployment Av baru pengganti Eset yaitu S1 ke seluruh client | Done | Medium | all | 2026-01-07 |  | 2026-01-13 | 95% | ada bberapa User blm
279 |  | Adjustment Out & IN atas Pesanan Bapenas Gramedia Matraman | Done | Medium | Buchori | 2026-01-14 |  | 2026-01-15 | 100%
280 |  | Pembuatan Location event 4 di WH 10123 Gramedia MM bekasi | Done | Medium | Prasetyo | 2026-01-14 |  | 2026-01-14 | 100%
281 |  | Adjusment OUT barang deadStok Graemdia Mega Bekasi 10186 | Done | Medium | Priyanta | 2026-01-14 |  | 2026-01-14 | 100%
282 |  | Adjustment Out Product Broken 10473 Gramedia Cibinong | Done | Medium | Widiarto | 2026-01-12 |  | 2026-01-13 | 100%
283
284
285
286
287
288

## Kanban board
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
KANBAN BOARD
Helpdesk Support Tracker | IT Support Tracker
7
| WIP limit is set at: | 4
|  | 0 | 5 | 0 | 0 | 2 | 113 | 1 | 159 | 0 | 0 | 0 | 0
|  | Backlog | In-Progress | Research | Q&A | Hold before final | Done | Pending | Complete |  |  |  |  | NOTES
| Stage | 0 | Medium | 0 | 0 | Medium | Medium | 0 | High | 0 | 0 | 0 | 0 | Columns turn gray when the WIP limit has been reached
| Start date |  | 2024-10-02 |  |  | 2024-09-03 | 2025-02-11 |  | 2024-08-21
| Task |  | Support Event Store Superindo Pulomas ( Pic Gramedia ARTHA GADING ) |  |  | Store In Store Yogya Sukabumi Suryakencana> 10499 Gramedia Sukabumi | Stock Opname RFID Gramedia PIM 18 & 25 Feb 2025 |  | Instalasi POS register Semesta Peslit
| Due date |  | 2025-05-15 | [5 empty] | 2024-08-23
| Work progress (%) |  | 1899-12-31 |  |  | 0.1 | 1899-12-31 |  | 1899-12-31
| Finish date |  | 2025-07-01 |  |  |  | 2025-02-18 |  | 2023-08-29
|  | 0 | Medium | 0 | 0 | Medium | High | 0 | Medium | 0 | 0 | 0 | 0
|  |  | 2025-05-26 |  |  | 2024-09-03 | 2025-05-05 |  | 2024-08-01
|  |  | Setting dogle wifi di gedung sebrang ruangan digital lt 5 |  |  | Store In Store Yogya Sumedang > 17110 Gramedia Subang | Konfigurasi IP Static di ruang Markom |  | Stock Opname Agustus 2024
2024-08-31
|  |  | 1899-12-31 |  |  | 0.1 | 1899-12-31 |  | 1899-12-31
|  |  | 2025-05-27 |  |  |  | 2025-05-06 |  | 2024-08-31
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | High | 0 | 0 | 0 | 0
[7 empty] | 2025-05-15 |  | 2024-08-25
[7 empty] | Penambahan Location Event 4 Store 10187 |  | Loading Persiapan Peslit Taman Ismail Marjuki 25 Agust 2024
2024-08-25
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-19 |  | 2024-08-25
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | Medium | 0 | 0 | 0 | 0
[7 empty] | 2025-05-15 |  | 2024-08-27
[7 empty] | Reset Email Gam227@gramedia.com |  | cancel SO-PO GAN, BKM,WAM yang tidak sama nilainya
2025-05-15
[7 empty] | 1899-12-31 |  | 1899-12-31
2024-09-24
|  | 0 | 0 | 0 | 0 | 0 | High | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14
Pendataan Device Register Aktiff terkait Licensi 365 bln Agustus 2025
2025-05-14
1899-12-31
2025-06-04
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | Medium | 0 | 0 | 0 | 0
[7 empty] | 2025-05-14 |  | 2024-09-02
[7 empty] | Penambahan Lines IJ Ownership Change menjadi 400 lines Uji coba |  | Test Firewall Karawaci & BSD tanpa Proxy
[7 empty] | 2025-05-15 |  | 2024-09-02
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-15 |  | 2024-09-16
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | High | 0 | 0 | 0 | 0
[7 empty] | 2025-05-15 |  | 2024-09-02
[7 empty] | MOvmennt Item Sampel permintaan MArkom IJGLK2505-000000897 |  | Posting Statment Buln Agustus 2024
[7 empty] | 2025-05-15 |  | 2024-09-02
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-19 |  | 2024-09-02
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | High | 0 | 0 | 0 | 0
[7 empty] | 2025-05-15 |  | 2024-09-02
[7 empty] | ADjustment OUT GLKU Request Raja Item proyek |  | Prosess Delivered So atas Order Online Agustus 2024
[7 empty] | 2025-05-15 |  | 2024-09-04
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-19 |  | 2024-09-09
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | High | 0 | 0 | 0 | 0
[7 empty] | 2025-05-19 |  | 2024-09-03
[7 empty] | Pnambahan location event4 Store 10117 |  | Store In Store Transamart Kota Casablanca > 10108 Matraman
[7 empty] | 2025-05-19 |  | 2024-09-23
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-19 |  | 2024-09-30
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | Medium | 0 | 0 | 0 | 0
[7 empty] | 2025-05-18 |  | 2024-09-05
[7 empty] | Adjustment Stock Opname Tahunan Gramedia HI 10372 |  | BA Kesalahan Rcv 10478 Dwi Maju POGAM2408-00313744 >email Audina
[7 empty] | 2025-05-25 |  | 2024-09-06
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-28 |  | 2024-10-09
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | Medium | 0 | 0 | 0 | 0
[7 empty] | 2025-05-19 |  | 2024-09-13
[7 empty] | Adjustment Stock Opname Tahunan Gramedia MM Bekasi 10123 |  | Support Pameran Gramedia Sale Resinda Karawang 14- 30 Sept 2024
[7 empty] | 2025-05-23 |  | 2024-09-14
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-05-27 |  | 2024-09-30
|  | 0 | 0 | 0 | 0 | 0 | Medium | 0 | Medium | 0 | 0 | 0 | 0
[7 empty] | 2025-05-19 |  | 2024-09-15
[7 empty] | Adjustment Stock Opname Tahunan Gramedia Pejaten 10454 |  | Support Pameran Gramedia Sale Botani Atrium Mall 23-Sept-6 Okt 2024
2024-09-23
[7 empty] | 1899-12-31 |  | 1899-12-31
[7 empty] | 2025-06-09 |  | 2024-10-06
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | 0 | 0
2024-09-06
Persiapan Penerimaan Gramedia The Park Sawangan 10174 di Depok
2024-09-15
1899-12-31
2024-10-23
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | 0 | 0
2024-09-09
Case Retturn So 10124 yang Nilainya tidak Sama dengan Invoice
2024-09-12
1899-12-31
2024-09-13
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | 0 | 0
2024-09-12
Relokasi 10127 Gramedia yogya mallioboro 12 Sept sudah Close
1899-12-31
2025-01-08
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | 0 | 0
2024-09-10
Migrasi Event1 to 81112 di JGC 27 Opname , 1 Oktober Migrasi ke 81112
2024-09-29
1899-12-31
2024-10-01
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Medium | 0 | 0 | 0 | 0
2024-09-04
Relokasi 10127 Gramedia yogya mallioboro 12 Sept sudah Close Opening 6 des 2024
1899-12-31
2024-12-06
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | High | 0 | 0 | 0 | 0
2024-10-02
support Event Sainsday Pim3 7-12 Okt 2024
2024-10-06
1899-12-31
2024-09-12

## Fields
FIELDS
Helpdesk Support Tracker | IT Support Tracker
| Project name | Stage | Priority | Person responsible | NOTES
| Helpdesk Support Tracker | Backlog | High | Widiarto | Once the WIP limit is reached exactly, any stage column
|  | In-Progress | Medium | Buchori | with that exact number of cards will gray out
|  | Research | Low | Sumitro | "Stage" supports up to 12 unique registers.
|  | Q&A | No priority | Sukiman | "Priority" and "Person responsible" can support more than 12 unique registers.
|  | Hold before final | Cancelled | Aat | If more rows are required for "Priority" and "Person responsible", add more rows above gray borderline.
|  | Done | Empty | Hamzah
|  | Pending |  | Prasetyo
|  | Complete |  | Santo Gultom
IVO
Gusri
Sutono
David A
Adi S
Hendry
Andhiek
Priyanta
Edy K
Mansyur
Muchsin
Nuralam
Rofiq
Agung
Raden Fadly
Limit for the maximum number of entries. Anything below this row will be ignored.

## Benefits
BENEFITS
Below are all the benefits included in the complete version of this spreadsheet. Join today and access our entire library of business resources.
Start today
Complete version comes with a 12-month calendar view, so you van view all your tasks by priority across the next 12 months.
Complete version includes a dashboard to track your wofklow's progress across each of your tasks.
Visualize your complete tasks against how many are left, as well as your total overdue.
View the breakdown of your total tasks by stage as well as total tasks by priority.
Account for tasks by their stage and their priority levels according to the team members responsible to identify bottlenecks and assess where to assign higher priority work.
View all upcoming tasks for the year summed up across each month to help view a whole year's worth of tasks at a glance.
And visualize your total progress towards completion across your entire workflow to gauge how far into your progress you still have left to accomplish - or how much you've accomplished so far.
With a progress dashboard and a 12-month calendar view, you have every visualization you need to manage your projects and workflow with ease.
Gain all these benefits when you join today... | Get spreadsheet
Errors and omissions liability (E&O): You Exec LLC makes no guarantee that the formulas, models, analysis, financial projections, estimates, graphs, reports, numbers, and any derivatives sourcing from this model are free of errors and omissions. Our financial modelers have audited this model to the best of their capabilities, yet You Exec LLC assumes no liability for erroneous outcomes derived from this financial model.
Copyright © You Exec LLC. All rights reserved.